Digitalization Portfolio — Status Report

Week 28  |  July 9, 2026

# Portfolio Assessment

| Initiative | Status | Key signal |
| --- | --- | --- |
| IBPROM Production | Live | Over 85% digital reports KPI in 2026; stable and widely implemented |
| IBPROM Topography | Live | 100% digital reporting for ICL data; non-ICL onboarding pending |
| IBPROM Geology | Live | Full 2026 data entry in progress |
| IBPROM v3 | Live | Released and stable; DB schema cleanup now underway |
| IBPROM DB Schema Cleanup | Scoped | Jira-tracked cleanup defined; not yet started |
| IBPROM v4 | Scoped | FSD complete; awaiting business approval and budget |
| IBPROM Shift Handover | Live (low adoption) | MVP live but not used; scope was oversimplified |
| Geotechnical Domains PowerApp | Live (blocked) | App works, but iPad enrollment blocker prevents use |
| PowerApp – IBPROM Middleware | UAT | Dev complete; awaiting confirmation to start testing |
| HR Payroll — Miners | Live (partial) | Rollout paused — awaiting v4 |
| HR Payroll — Brigada | Pilot in progress | Brigada pilot underway with Mine Manager |
| HR Payroll Fiori | UAT | E2E test repeatedly blocked by IPQ errors |
| Truck Portal MMA 44t | Live | Phase 2 functional design open |
| Truck Portal — Cognito Auth Migration | Ready for rollout | Built and documented; rollout to users pending |
| Queue Management System | UAT | UAT underway; targeting June 2026 go-live |
| QMS Public Site | Scoped | Public wiki + docs site for QMS; scoped, not started |
| SAL VESTA RPA Automation | Pending gate | Awaiting IT approval + RPA estimate |
| SAP Logistics — DCA Digitization (SIMPLE) | Architecture / pending gate | Public-URL API question delegated to SAP team; Oct 2026 deadline |
| IBPROM – SAP HR Middleware | Pending scope | Master data not synced; SAP needs to be source of truth |

IBPROM PLATFORM

| IBPROM Production | LIVE |
| --- | --- |

Status: LIVE — Stable and widely implemented; over 85% digital reports KPI in 2026

- Digital reports KPI has exceeded 85% for 2026, reflecting strong and sustained adoption across production teams

- Product is stable and widely implemented across the business, with no open issues at this time

- Next steps: monitor KPI and adoption to sustain current performance

| IBPROM Topography | LIVE |
| --- | --- |

Status: LIVE — 100% digital reporting for ICL data; non-ICL onboarding pending

- Digital reporting has reached 100% coverage for ICL-operated machines

- Remaining gap: onboarding of contracted/external operator machines (non-ICL) is still pending, with no firm timeline set yet

- Next steps: define an onboarding plan and timeline for non-ICL contracted operators

| IBPROM Geology | LIVE |
| --- | --- |

Status: LIVE — Go-live executed; full 2026 data entry in progress

- Go-live formally executed following successful UAT and resolution of all issues from the previous rollback (machinery data inconsistencies, form usability)

- Geologists are actively entering data in IBPROM and have committed to capturing all 2026 records from January onward — ensuring a complete and continuous dataset from the start of the year

- Next steps: monitor adoption and data quality

| IBPROM v3 | LIVE |
| --- | --- |

Status: LIVE — Released and stable; UAT closed successfully, full rollout complete

- UAT completed successfully with end users, validating new interfaces (Geology module UI) and confirming compatibility with the Power BI data model — synchronization process unaffected

- Release delivered on the two extended-scope items validated during UAT:

  - Production paper dependency: historical pane access extended to other mine roles, unlocking full digital traceability

  - Topography digital adoption: browser-based workaround validated in the real mine environment — topography supervisors now using multi-sketch tabs in production

- Brigada flow validated with HR as part of the release; both HR Payroll tracks now able to build on the v3 improvements

- Next steps: monitor stability post-release; support IBPROM v4 scoping for HR Payroll Miners rollout

| IBPROM DB Schema Cleanup | SCOPED |
| --- | --- |

Status: Scoped — Jira-tracked cleanup defined; not yet started

- Cleanup covers naming convention inconsistencies, string-stored foreign key anti-patterns, and column-name typos across multiple form tables

- Fully scoped in Jira; work has not yet started

- Next steps: prioritize against active IBPROM/v4 work; begin execution

| IBPROM v4 | SCOPED |
| --- | --- |

Status: Scoped — FSD complete; awaiting business approval and budget confirmation

- Functional Specification Document written and completed; main feature scoped is work instructions

- Awaiting business approval of the FSD and confirmation of budget before development can start

- Next steps: secure business approval; confirm budget; schedule development kickoff

| IBPROM Shift Handover | LIVE (LOW ADOPTION) |
| --- | --- |

Status: MVP live — released but not adopted by the business

- MVP released, but usage by the business has not materialized

- Root cause: scope was oversimplified to accelerate delivery, resulting in a product that does not add enough value to the business as-is

- Key dependencies: two contributing projects gate this initiative's value — the IBPROM – SAP HR Middleware (unlocks personnel management) and the PowerApp – IBPROM Middleware (currently in UAT)

- Next steps: rescope with the value gaps identified from the MVP; align delivery with progress on both the SAP HR Middleware and PowerApp Middleware projects

| Geotechnical Domains PowerApp | LIVE (BLOCKED) |
| --- | --- |

Status: Live — functional, but blocked from use by a device enrollment issue

- App itself works well; business feedback on functionality has been positive

- Reporting output is not compatible with the business's current workflow — a gap identified after go-live

- Blocking issue: the business uses iPads that are not enrolled in company IT, making it impossible to operate the PowerApp on those devices

- Local IT has reportedly been unable to enroll the devices into the ICL cloud

- Next steps: resolve iPad enrollment with local IT; revisit reporting format against the business's actual workflow

| PowerApp – IBPROM Middleware | UAT |
| --- | --- |

Status: UAT — development complete; awaiting confirmation to begin testing

- Development completed by the team

- Waiting on confirmation from the development team to start UAT

- Key dependency: this is another major contributing factor to the IBPROM Shift Handover project

- Next steps: get confirmation from development team; schedule and begin UAT

HR PAYROLL DIGITALIZATION

| Shift Hours — Production / Miners | LIVE (PARTIAL) |
| --- | --- |

Status: LIVE — Rollout still paused at 50%; IBPROM v3 now live but v4 requirements still pending

- Digital process stable

- Rollout to remaining mine teams remains on hold — IBPROM v3 has now released, but the specific data entry controls, approval flow visibility, and cost monitoring improvements this track needs are being tracked separately for v4

- A structured end-to-end review is pending to allocate responsibilities correctly: IBPROM (operational data entry controls), SAP (authoritative validations), Power BI (cost visibility and exception monitoring)

- Requirements emerging from active rollout reflect genuine user pain points and are being tracked separately from the planned v4 scope

- Next steps: complete system responsibility mapping; define mandatory vs. deferrable requirements; package into IBPROM v4

- Target: full mine-team rollout Q2 2026, contingent on v4 delivery

| Shift Hours — Brigada / Services | PILOT IN PROGRESS |
| --- | --- |

Status: Pilot underway with Brigada — hybrid flow validated; SAP ingestion checked

- Important nuance: Brigada workflow starts on paper (partes filled by supervisors, entered centrally into IBPROM by an administrative) — digital chain runs from IBPROM entry onward through approval and SAP ingestion

- Rollout strategy session held with the Brigada Mine Manager — pilot scope agreed and pilot now underway; progressive rollout to follow

- Even in hybrid form, this go-live enables the Brigada Mine Manager to work with Power BI data and KPIs for the first time

- Next steps: monitor pilot results; plan progressive rollout and training sessions for remaining Brigada teams

| HR Payroll Fiori | UAT |
| --- | --- |

Status: UAT — end-to-end test repeatedly blocked by IPQ system errors

- E2E test has not been completed successfully due to recurring errors in IPQ

- No direct access to IPQ, which means each attempt requires scheduling user acceptance tests with real users; these sessions have repeatedly failed due to the underlying IPQ issues, not the test design

- Tech teams have applied fixes after each failed round, but a full E2E pass has not yet been achieved

- Next steps: get direct IPQ visibility or a dedicated diagnostic session with the tech team ahead of the next user test; avoid scheduling further live user tests until the underlying IPQ issue is confirmed resolved

LOGISTICS & TRUCK MANAGEMENT

| Truck Portal MMA 44-Ton | LIVE |
| --- | --- |

Status: LIVE — In production; Phase 2 functional design in progress

- Production deployment completed; the 44-ton capacity flow is live and operational

- Phase 2 scope initiated — working sessions with SAP (NTT Data), Logistics, VIDMAR, and ARIPLAN underway

- Four functional areas identified for Phase 2:

  - Axle management: axle count travels correctly from the reservation web to middleware, but SAP is using internal master data instead — causing inconsistencies in loading logic and downstream systems

  - Load capacity logic: SAP axle-to-maximum-load rules need revision

  - Net weight calculation: currently done manually at the entry weighbridge — automation would eliminate errors and improve operational efficiency

  - Reservation data completeness: fields available in the web (transport card, driver ID, carrier details) not always persisted in SAP — forcing logistics operators to consult external sources

- Active incident under investigation: net weight not appearing in TRS.NET for a specific case — likely caused by message arrival ordering between Operational status update and LoadingInformation update; VIDMAR asked to validate

- Next steps: validate SAP message ordering with VIDMAR; confirm Phase 2 functional scope with all teams; plan development start

| Truck Portal — AWS Cognito Auth Migration | READY FOR ROLLOUT |
| --- | --- |

Status: Documentation complete — migration built, not yet rolled out to users

- Authentication migrated from the previous scheme to AWS Cognito with email-based one-time codes

- User communication and supporting documentation completed in Spanish

- Next steps: schedule and execute rollout to users

| Queue Management System (Suria Plant) | UAT |
| --- | --- |

Status: UAT — Development completed; UAT underway ahead of June 2026 go-live

- API contract closed and mock APIs delivered by VIDMAR as committed; development completed on that foundation

- Azure infrastructure session completed; VIDMAR server deployed in Azure

- New state model in place: PLANNED_RESERVATION / ACTIVE_RESERVATION — handles daily queue trigger and spontaneous/EXW truck arrivals; TRS.NET remains sole source of truth

- SMS confirmed as primary channel; URL-based digital confirmation adopted as the inbound reply mechanism — resolves the international SMS routing risk identified

- UAT sessions in progress with VIDMAR and ICL dev team

- Next steps: complete UAT sign-off; prepare for go-live

- Target: June 2026 go-live

| QMS Public Site | SCOPED |
| --- | --- |

Status: Scoped — not yet started

- Scope defined: a small public-facing website hosting a wiki and a set of public documents directly tied to the QMS project

- Work has not yet started

- Next steps: prioritize against QMS core delivery; begin build once scheduled

SAP LOGISTICS — REGULATORY DIGITIZATION

| DCA Digitization — Plataforma SIMPLE Integration | ARCHITECTURE / PENDING GATE |
| --- | --- |

Status: Architecture defined — critical integration question outstanding; regulatory deadline October 2026

- Mandatory digitization of the Documento de Control Administrativo (DCA) applies from October 2026; architecture favors a middleware-over-SAP approach integrating with Plataforma SIMPLE, the free Ministry of Transport-backed platform

- Critical open question: whether SIMPLE's Documentation API serves QR-linked documents via a public, unauthenticated URL — required by regulation. Question has been delegated to the SAP team for follow-up with SIMPLE support; no reply yet

- Entity registration on SIMPLE not yet started — pending an FNMT digital representation certificate; Integration Kit download still to be requested

- Next steps: follow up on the SIMPLE public-URL question; secure FNMT certificate and register the entity; download Integration Kit once registered

PROCESS AUTOMATION

| SAL VESTA Order Automation (RPA → SAP) | PENDING GATE |
| --- | --- |

Status: Functional design closed — Pending effort estimation and IT management approval to proceed

- Functional design (DF v3, NTT Data) reviewed, confirmed complete, and approved by business — no additional functional development required

- Agreed solution: hybrid RPA + SAP approach

  - RPA monitors incoming emails, extracts data from SAL VESTA PDF orders, converts to XML, and deposits files in the designated SAP directory

  - SAP processes the XML to create sales orders automatically, including duplicate prevention and execution logging

- Notification design closed: SAP sends the order PDF automatically to the requester; no custom internal notification development needed — users can consult created orders directly via standard SAP transactions

- Business validation provided; development approval pending final IT management sign-off together with RPA effort estimation

- Next steps: receive RPA effort estimation; complete overall cost and planning; obtain IT management approval to proceed with development

CROSS-SYSTEM INTEGRATION

| IBPROM – SAP HR Middleware | PENDING SCOPE |
| --- | --- |

Status: Pending scope — master data synchronization gap identified between IBPROM and SAP HR

- IBPROM and SAP HR are already connected via middleware for payroll data, but master data between the two systems is not synchronized

- Target design: SAP master data should become the source of truth in both systems, removing the current inconsistency risk

- Strategic importance: this project is a key unlock for IBPROM Shift Handover, since it enables the personnel management capability that initiative needs to deliver real value

- Next steps: scope the master-data synchronization approach; align with SAP HR team on source-of-truth model; sequence against Shift Handover rescoping